## Sheet1
ID | Task | Priority | Effort Estimation Hrs | Status | Assigned To | Sprint | Due Date | Notes / Comments
1 | Kickoff Meeting | High | 2 | Done | Cameron | 1 | 2025-04-07 | Conduct project kickoff and define initial goals
2 | Receive CSV Data | High | 1 | Done | Jory | 1 | 2025-05-11 | Collect Breakaway data from Jory
3 | Gather CMS Requirements | High | 3 | Done | Rand & Melina | 1 | 2025-05-11 | Obtain field requirements from Rand & Melina
4 | Design Data Mapping | High | 5 | Done | Tabitha | 1 | 2025-05-11 | Map CSV fields to Wix CMS structure
5 | Set Up Google Environment | High | 6 | Done | Christopher | 1 | 2025-05-11 | Configure Google environment for data processing and potential automation backend
6 | Build Python Parsing Script | High | 8 | Done | Adam/Carita | 2 | 2025-05-25 | Create script using Python + NumPy to parse CSVs and prepare data for CMS
7 | Implement Data Validation Logic | Medium | 5 | Done | Mary | 2 | 2025-05-25 | Add validation layer to flag invalid or inconsistent data before ingesting
8 | Configure Wix CMS Collections | Medium | 4 | Done | Zapier | 2 | 2025-05-25 | Set up Wix Collections to accept structured input from ingestion pipeline
9 | Create Dynamic Frontend Elements | Medium | 6 | Done | Zapier | 2 | 2025-05-25 | Use Wix Repeaters or dynamic lists to display data by sport, player, and stat
10 | Develop Bucketing Logic by Sport | Medium | 5 | Done | Adam/Carita | 3 | 2025-06-08 | Organize data templates by sport type (e.g., football, basketball)
11 | Integrate Mock Data from GrindGeek | Low | 3 | Done | All | 3 | 2025-06-08 | Use mock data from GrindGeek to test multi-source compatibility
12 | Conduct UAT with Client | High | 4 | Done | Mary | 3 | 2025-06-08 | Perform final review with FanView team to confirm functionality and UX
13 | Fix Errors | High | 6 | Done | Adam/Carita | 3 | 2025-06-08 | Resolve issues discovered during testing
14 | Deploy to FanView | High | 4 | Done | All | 3 | 2025-06-08 | Finalize deployment of the system
15 | Training & Docs | Medium | 5 | Done | Tabitha/Carita |  | 2025-06-08 | Provide documentation and system training
16 | Final Walkthrough & Feedback Session | Medium | 2 | Done | All | 3 | 2025-06-08 | Host last Zoom with client to hand off, answer questions, and collect feedback